## Sheet1
Task |  |  |  | Date of | Duration | January, 2008 |  |  | February, 2008 |  |  |  |  | March, 2008 |  |  |  |  | April, 2008
|  |  | Owner | Completion | (Weeks) | 2008-01-18 | 2008-01-25 | 2008-02-01 |  | 2008-02-08 | 2008-02-15 | 2008-02-22 | 2008-02-29 | 2008-03-07 | 2008-03-14 | 2008-03-21 | 2008-03-28 | 2008-04-04 |  | 2008-04-11 | 2008-04-18 | 2008-04-25 | 2008-05-02
Obtain Server |  |  | Derrick, Patrick | 2008-01-18 | 1
Install LAMP & Trac |  |  | Derrick | 2008-01-25 | 2
| Install & Setup LAMP |  |  |  | 1.5
| Configure SVN, Trac, Wiki |  |  |  | 1.5
Module-Module Interface Design |  |  | All | 2008-02-01 | 2
| User Interface |  |  |  | 0.5
| Database |  |  |  | 1
| Controller + Optimizer |  |  |  | 1
Framework |  |  | Derrick, Patrick |  | 2.5
| User Profile Management |  | Patrick, Garrett | 2008-02-08 | 2.5
|  | Personal Info |  |  | 1
|  | Blacklist |  |  | 1
|  | Ride Requests (Drivers & Riders) |  |  | 2
| Interfacing Database Tables |  | Yoni, Patrick | 2008-02-08 | 2
|  | Ride Requests |  |  | 1
|  | Results |  |  | 1.5
| Google Maps Queries |  | Derrick | 2008-02-08 | 2
| Controller-Database Interaction |  | Yoni, Patrick | 2008-02-08 | 1
Backend for UI/Optimization |  |  | Derrick | 2008-02-29 | 3
| User Notification |  |  |  | 1
User Interface Frontend |  |  | Patrick | 2008-02-29 | 4
| Google Maps Visualization |  | Yoni, Derrick | 2008-02-22 | 2
| Map-Based Interactivity |  | Yoni, Derrick | 2008-02-29 | 2
| Site Map & Page Templates |  | Garrett, Patrick | 2008-02-29 | 1
Optimizer |  |  | Yoni | 2008-03-21 | 8
| Control Module |  | Yoni | 2008-03-21 | 2
| Search Space Reduction Function |  | Yoni, Derrick | 2008-03-14 | 2
| Optimization Algorithms |  | Yoni | 2008-03-21 | 8
|  | Genetic | Garrett, Patrick | 2008-03-14 | 7
|  | Brute Force | Yoni | 2008-03-07 | 5
|  | Bipartite Graph Matching | Derrick | 2008-03-14 | 7
|  | Iterative Bipartite Graph Matching | Derrick | 2008-03-21 | 7
Testing |  |  | Garrett | April | 11
| Test Case Generation |  | Garrett | 2008-02-29 | 2
| Algorithm Scoring Function |  | Garrett | 2008-03-21 | 2
| Algorithm Visualization |  | Garrett, Patrick | 2008-03-21 | 4
Testing |  |  | Garrett | April | 11
| Test Case Generation |  | Garrett | 2008-02-29 | 2
| Algorithm Scoring Function |  | Garrett | 2008-03-21 | 2
| Algorithm Visualization |  | Garrett, Patrick | 2008-03-21 | 4
EE464 Deliverables
| Proposal |  | Yoni, Garrett | 2008-01-31 | n/a
| Design Review |  | Derrick, Patrick | 2008-02-14 | n/a
| Design Review Oral Presentation |  | Yoni, Derrick | 2008-02-14 | n/a
| Intellectual Property Report |  | Yoni, Derrick | 2008-02-28 | n/a
| Pre-Demo Performance |  | All | 2008-02-28 | n/a
| Oral Progress Report |  | Garrett, Patrick | 2008-02-28 | n/a
| Final Demo |  | All | 2008-04-01 | n/a
| Oral Final Presentations I |  | All | 2008-04-29 | n/a
| Final Report |  | All | 2008-05-01 | n/a
| Oral Final Presentation II |  | All | 2008-05-01 | n/a